|  |  |  |
| --- | --- | --- |
| Grant Health ••• | | |
| **NLP Grant:**  **Milestones:**  1. 173% of Biodiveristy (WoNS weeds) treated  2. 170% of Coastal waterway weeds treated  3. 150% of revegetation achieved/allocated  4. 67% of ferals dispatched  **Highlights:**  We have already treated approximately 170% of the spatial requirements for weeds under this program  **Concerns:**  Need to increase fence allocations. Currently allocated 53% and 62% of the way through program  **Financial:**  We have spent a limited amount on the expenditure side of this grant but completed a lot of the outcomes. I would ask if there is any space in this grant to value add in the requirements. | **REI Grant:**  **Milestones:**  1. 16 % of fencing has been achieved/allocated  2. 15% of re vegetation has been allocated  3. Workshops are on target  **Highlights:**  Engagement with dairy farmers increasing. Fencing dairy drains.  **Concerns:**  NIL  **Financial:**  Early in the Grant, but again looks like Expenditure is lagging our progress. Low hanging fruit has been captured. Have approached all dairies in catchment as a priority for future works under this grant. | **SNRMO – SGW Grant:**  **Milestones:**  We have met all pre grant criteria conditions since last meeting. We will be holding a Project Kick Off meeting with Green Skills and agro foresters next month to plan works  **Highlights:**  NIL at this time  **Concerns:**  NIL at this time |
|  | **SNRMO – Lindesay Link Grant:**  **Milestones:**  We have signed all SNRMO contracts and received our first instalment payment of $30,000. Pest controller has been contracted. Project Kick Off meeting scheduled **for 16 March.**  **Concerns:**  NIL at this time.  **Financial:**  Nothing to highlight Financially. Performing over expectations. | **NOTES:**   * **REI (Regional Estuaries Initiative)** $605,000 over 4 years to reduce nutrients in Wilson Inlet with stock exclusion fencing (40 km) and revegetation (12 Ha) * **NLP Grant (National Landcare Program** $371.726 over 3 years focussing on biodiversity, soil health and coastal waterways * **SNRMO – SGW GRANT (Sydney Golden Wattle)** – $30,000. This is a follow up of SGW works from last year in lower catchment and adding 3 agroforestry blocks adjacent quality rem veg in upper catchment * **SNRMO-Lindesay Link Grant -** $100,000 over 20 months. This grant will be identifying and implementing a baiting program in black-glove wallaby and honey possum habitat throughout the catchment. We have contracted a licensed pest controller to carry out works. |